## Cover Page
Bill Payment System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Neeraj Nandan
| Role | Product Owner
Signature
Date
Project ID: Car Servicing | <Hyd19IJ001/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Bill Payment System Project ID: HYD19IJ001/ C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
1 | 1.01 | When the user clicks on the registration link, system should re-direct to registration form and provide two options: Register as Customer Register as vendor | Neeraj | 1 | 1 | 1 | 0.5 |  |  |  | Completed
1 | 1.02 | User to fill the basic attributes: First Name Last Name Age Gender Contact NumberUser to fill the basic attributes: First Nam,e Last Name, Age, Gender, Contact Number, Email Address, PAN, Aadhar Number, User Id, Password | Neeraj | 1 | 1 | 1 |  |  |  |  | Completed
1 | 1.03 | Clicking ‘Submit’ button should validate the datatype constraints for each field. | Neeraj | 1 | 0.5 | 0.5 |  |  |  |  | Completed
1 | 1.04 | User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
1 | 1.05 | Post-successful field validation, save the information in the database | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
2 | 2.01 | A registered user – is able click ‘Login’ link, after keying in ‘UserID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
2 | 2.02 | If a registered user – is unable to login and get his credentials authenticated, The user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
3 | 3.01 | Vendor clicks on the “Register Vendor” button | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
3 | 3.02 | Portal to display a form to enter the below details: Name of the Vendor, Company Reg. No, Vendor Type, Address, Country, State, Email Address, Contact number, Web site, Certificate Issued Date, Certificate Validity date, Year of Establishment | Neeraj | 1 | 1 | 1 | 0.5 |  |  |  | Completed
3 | 3.03 | The display form should have buttons to “Register” or “Reset” the fields | Neeraj | 1 | 1 | 1 | 1 |  |  |  | Completed
3 | 3.04 | Clicking on Register button should save the details to the database and display the message “Vendor registered successfully” | Neeraj | 1 |  |  | 0.5 |  |  |  | Completed
3 | 3.05 | Clicking “Reset” button should clear all the fields and allow Vendor to enter new details | Neeraj | 1 |  |  | 1 |  |  |  | Completed
7 | 7.01 | User clicks on the option to Pay Bills | Neeraj | 1 |  |  | 1 |  |  |  | Completed
7 | 7.02 | Portal to display a dropdown button to select the type of bill to be payed: Electricity, Telephone, DTH, Insurance, Tax, Credit Card, Loan account, Others | Neeraj | 1 |  |  | 1 | 1 |  |  | Completed
7 | 7.03 | Post the bill type is selected, Portal to verify the registered/updated information in the Database and the pending amount to be payed. | Neeraj | 1 |  |  | 1 | 1 |  |  | Completed
7 | 7.04 | If the details not are not available in the database display form based on the selected bill type and allow the user to enter the details | Neeraj | 1 |  |  |  | 1 | 1 |  | Completed
7 | 7.05 | User to select the payment method: Credit/Debit Card, Internet Banking, PayTm, Google Pay, e-Wallet | Neeraj |  |  |  |  | 1 | 1 |  | Completed
7 | 7.06 | Based on the selected payment type, portal to display the form to enter the required details | Neeraj |  |  |  |  | 1 | 1 | 1 | Completed
7 | 7.07 | Portal to process the payment through vendor payment gateway | Neeraj | [5 empty] | 1 | 1 | Completed
7 | 7.08 | Validate the provided details against the banks and display a message “Bill payement Successful” | Neeraj | [5 empty] | 1 | 0.5 | Completed
7 | 7.09 | If the entered details do not match display message “Enter correct details” | Neeraj | [6 empty] | 1 | Completed
|  | Total |  | 16 | 9.5 | 9.5 | 11.5 | 5 | 5 | 3.5
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A